## Sheet1
Systems Capstone: Gannt Chart
👺The Goblins 👺
Sameer Dandekar, Nathan Kennedy, Ankita Khera, Rachel Kitchen, Niles Rogoff
| February | [16 empty] | March | [30 empty] | April
| Done | ❤️ | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 🍀 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Milestones | [23 empty] | Spring Break
Buying/selling tickets
Entering the ticket lottery
Withdrawing from the lottery
Receiving a ticket from the lottery
MVP
Auction | bar: 20
Incentive-based rewards/penalties | bar: 27
Mobile app | bar: April 10 to April 12
QR codes | bar: April 17
Testing | bar: April 24
Tasks
Back-end
Set up AWS account, EC2 instance, nodeos
Design data structures for EOSIO tables
Design API for smart contract (actions, arguments, etc...)
Install eosio.token contract, create token HTK with 2 digits of precision
Implement smart contract tables and actions for MVP functionality
Create deployment pipeline for smart contract
Write python library (libgoblin) to support pulling data from EOSIO
Set up web server pulling dynamic data from libgoblin (www)
Write ricardian clauses and contracts for smart contract and associated actions
Update smart contract to prevent purchase of tickets if in lottery, and vice versa
Add methods for frontend actions to libgoblin (major integration challenge)
Design API and data structures for auctions, implement | bar: 18 to 20
Design API and data structures for incentive-based rewards/penalties, implement | bar: 18 to 27
Assist with mobile dev, update integration as needed | bar: 23 to April 12
Design API and data structures for QR codes, implement | bar: 30 to April 17
Test for security issues, edge cases, resolve errors. Revise unit tests as needed. | bar: April 11 to April 17; April 20 to April 24
Front-end
Learn frameworks (Mako templates, research JS frameworks)
Identify pages and functions
Create page skeletons
Create website design mockups
Adapt skeletons to mockups
Auction | bar: 18 to 20
Incentive-based rewards and penalties | bar: 23 to April 3
QR codes | bar: April 6 to April 17
Mobile design | bar: 18 to 20
Mobile development (iOS) | bar: 18 to April 12
Mobile development (Android) | bar: 30 to April 12
Test workflows and refine unit tests for web page/mobile app | bar: April 11 to April 24
| Design Phase |  |  |  | Implementation Phase | [5 empty] | Testing Phase
Sameer Dandekar
Nathan Kennedy
Ankita Khera
Rachel Kitchen
Niles Rogoff